## IGNORE
Phase | Task ID | Task Name | Description | Command/Action | Expected Result | Status | Notes | Priority | Estimated Time
1. Prerequisites | 1.1 | Verify Kubernetes Cluster | Check if Kubernetes cluster is accessible | kubectl cluster-info | Cluster info displayed |  |  | Critical | 2 min
1. Prerequisites | 1.2 | Check Kubernetes Nodes | Verify all nodes are ready | kubectl get nodes | All nodes in Ready state |  |  | Critical | 2 min
1. Prerequisites | 1.3 | Verify Helm Installation | Check if Helm is installed | helm version | Helm version displayed |  |  | Critical | 1 min
1. Prerequisites | 1.4 | Check kubectl Access | Verify kubectl can access cluster | kubectl get namespaces | List of namespaces displayed |  |  | Critical | 1 min
1. Prerequisites | 1.5 | Verify Storage Class | Check if storage class exists | kubectl get sc | Storage class available |  |  | High | 2 min
1. Prerequisites | 1.6 | Check Available Resources | Verify cluster has enough resources | kubectl top nodes | CPU/Memory availability shown |  |  | High | 2 min
2. SSL Certificates | 2.1 | Locate SSL Certificates | Find existing SSL certificates | ls -la /path/to/ssl/ | Certificate files found |  |  | Critical | 5 min
2.1 | 2.2 | Verify Certificate Validity | Check if certificates are valid | openssl x509 -in cert.crt -text -noout | Certificate details displayed |  |  | Critical | 3 min
2. SSL Certificates | 2.3 | Create TLS Secret | Create Kubernetes TLS secret from certificates | kubectl create secret tls emqx-tls --cert=cert.crt --key=cert.key -n platform | Secret created |  |  | Critical | 3 min
2. SSL Certificates | 2.4 | Verify Secret Creation | Confirm TLS secret exists | kubectl get secret emqx-tls -n platform | Secret found |  |  | Critical | 1 min
3. Namespace Setup | 3.1 | Create Platform Namespace | Create namespace for EMQX deployment | kubectl create namespace platform | Namespace created |  |  | Critical | 1 min
3. Namespace Setup | 3.2 | Verify Namespace | Check if namespace exists | kubectl get namespace platform | Namespace active |  |  | Critical | 1 min
4. EMQX Operator | 4.1 | Add EMQX Helm Repo | Add EMQX chart repository | helm repo add emqx https://repos.emqx.io/charts | Repository added |  |  | Critical | 2 min
4. EMQX Operator | 4.2 | Update Helm Repos | Update Helm repository cache | helm repo update | Repository updated |  |  | Critical | 1 min
4. EMQX Operator | 4.3 | Create Operator Namespace | Create namespace for EMQX operator | kubectl create namespace emqx-operator-system | Namespace created |  |  | Critical | 1 min
4. EMQX Operator | 4.4 | Install EMQX Operator | Deploy EMQX operator via Helm | helm install emqx-operator emqx/emqx-operator -n emqx-operator-system --create-namespace | Operator installed |  |  | Critical | 5 min
4. EMQX Operator | 4.5 | Wait for Operator Ready | Wait for operator pods to be ready | kubectl wait --for=condition=Ready pod -l control-plane=controller-manager -n emqx-operator-system --timeout=300s | Pod ready |  |  | Critical | 3 min
4. EMQX Operator | 4.6 | Verify Operator Installation | Check operator pods are running | kubectl get pods -n emqx-operator-system | All pods running |  |  | Critical | 2 min
5. EMQX Configuration | 5.1 | Create EMQX YAML Config | Prepare emqx-op.yaml configuration file | vi emqx-op.yaml | Config file created with TLS, replicas, resources |  |  | Critical | 15 min
5. EMQX Configuration | 5.2 | Configure Cluster Size | Set core nodes (2) and replicant nodes (1) | Edit emqx-op.yaml | Replicas configured |  |  | High | 5 min
5. EMQX Configuration | 5.3 | Configure TLS Listeners | Configure MQTT, MQTTS, WS, WSS listeners | Edit emqx-op.yaml listeners section | TLS configured for port 8883 and 8084 |  |  | Critical | 10 min
5. EMQX Configuration | 5.4 | Configure Resource Limits | Set CPU and memory limits/requests | Edit emqx-op.yaml resources section | Resources defined |  |  | High | 5 min
5. EMQX Configuration | 5.5 | Configure Persistence | Set up persistent storage for EMQX | Edit emqx-op.yaml volumeClaimTemplates | Storage configured |  |  | High | 5 min
6. EMQX Deployment | 6.1 | Apply EMQX Configuration | Deploy EMQX cluster | kubectl apply -f emqx-op.yaml | EMQX resources created |  |  | Critical | 3 min
6. EMQX Deployment | 6.2 | Monitor Pod Creation | Watch pods being created | kubectl get pods -n platform -w | Pods creating |  |  | High | 5 min
6. EMQX Deployment | 6.3 | Wait for EMQX Ready | Wait for all EMQX pods to be ready | kubectl wait --for=condition=Ready pod -l apps.emqx.io/instance=emqx -n platform --timeout=600s | All pods ready |  |  | Critical | 10 min
6. EMQX Deployment | 6.4 | Verify EMQX Custom Resource | Check EMQX CR status | kubectl get emqx -n platform | EMQX running |  |  | Critical | 2 min
6. EMQX Deployment | 6.5 | Check Pod Logs | Review logs for any errors | kubectl logs emqx-core-0 -n platform | No critical errors |  |  | High | 3 min
7. Service Exposure | 7.1 | Check Services Created | Verify EMQX services | kubectl get svc -n platform | Services created |  |  | Critical | 2 min
7. Service Exposure | 7.2 | Configure LoadBalancer | Change services to LoadBalancer type | kubectl patch svc emqx-dashboard -n platform -p '{""spec"":{""type"":""LoadBalancer""}}' | LoadBalancer assigned IP |  |  | High | 5 min
7. Service Exposure | 7.3 | Verify LoadBalancer IPs | Check external IPs assigned | kubectl get svc -n platform | grep emqx | External IPs displayed |  |  | High
7. Service Exposure | 7.4 | Setup Port Forwarding (Alternative) | Set up port forwarding if LoadBalancer not available | kubectl port-forward svc/emqx-dashboard -n platform 18083:18083 --address 0.0.0.0 & | Port forward active |  |  | Medium | 3 min
7. Service Exposure | 7.5 | Configure Ingress (Optional) | Set up ingress for dashboard | kubectl apply -f mqtt-dash-ingress.yaml | Ingress created |  |  | Low | 10 min
8. Testing - MQTT | 8.1 | Access Dashboard | Open EMQX dashboard in browser | http://<IP>:18083 | Dashboard accessible |  |  | Critical | 2 min
8. Testing - MQTT | 8.2 | Login to Dashboard | Login with default credentials | Username: admin, Password: public | Login successful |  |  | Critical | 1 min
8. Testing - MQTT | 8.3 | Check Cluster Status | Verify cluster nodes in dashboard | Dashboard → Cluster → Overview | All nodes shown |  |  | High | 2 min
8. Testing - MQTT | 8.4 | Test MQTT via Dashboard | Use WebSocket client in dashboard | Dashboard → Diagnose → WebSocket Client | Connection successful |  |  | Critical | 5 min
8. Testing - MQTT | 8.5 | Subscribe to Test Topic | Subscribe to test/# topic | Subscribe in WebSocket client | Subscription active |  |  | High | 2 min
8. Testing - MQTT | 8.6 | Publish Test Message | Publish message to test topic | Publish in WebSocket client | Message received |  |  | High | 2 min
8. Testing - MQTT | 8.7 | Install mosquitto-clients | Install MQTT testing tools | sudo apt install -y mosquitto-clients | Tools installed |  |  | High | 3 min
8. Testing - MQTT | 8.8 | Test MQTT via CLI | Test MQTT using mosquitto_pub | mosquitto_pub -h <IP> -p 1883 -t test/mqtt -m 'test' | Command successful |  |  | Critical | 3 min
9. Testing - MQTTS | 9.1 | Extract CA Certificate | Export CA certificate from secret | kubectl get secret emqx-tls -n platform -o jsonpath='{.data.ca.crt}' | base64 -d > /tmp/emqx-ca.crt | Certificate saved |  |  | Critical
9. Testing - MQTTS | 9.2 | Verify Certificate | Check certificate validity | openssl x509 -in /tmp/emqx-ca.crt -text -noout | Certificate valid |  |  | High | 2 min
9. Testing - MQTTS | 9.3 | Test MQTTS Connection | Test MQTT with TLS encryption | mosquitto_pub -h <IP> -p 8883 -t test/mqtts -m 'secure' --cafile /tmp/emqx-ca.crt --insecure | Command successful |  |  | Critical | 3 min
9. Testing - MQTTS | 9.4 | Subscribe with MQTTS | Test MQTTS subscription | mosquitto_sub -h <IP> -p 8883 -t test/mqtts/# --cafile /tmp/emqx-ca.crt --insecure -v | Subscription working |  |  | High | 3 min
9. Testing - MQTTS | 9.5 | Check Listener Status | Verify all listeners are active | kubectl exec -it emqx-core-0 -n platform -- emqx_ctl listeners | All listeners running |  |  | Critical | 3 min
10. Verification | 10.1 | Verify All Pods Running | Check all EMQX pods are healthy | kubectl get pods -n platform | All pods running 1/1 or 2/2 |  |  | Critical | 2 min
10. Verification | 10.2 | Check Resource Usage | Monitor CPU and memory usage | kubectl top pods -n platform | Resources within limits |  |  | High | 2 min
10. Verification | 10.3 | Verify Persistent Storage | Check PVCs are bound | kubectl get pvc -n platform | All PVCs bound |  |  | High | 2 min
10. Verification | 10.4 | Test Dashboard API | Test EMQX API endpoint | curl http://<IP>:18083/api/v5/nodes -u admin:public | API response received |  |  | High | 2 min
10. Verification | 10.5 | Check Logs for Errors | Review logs for any issues | kubectl logs -l apps.emqx.io/instance=emqx -n platform --tail=50 | No critical errors |  |  | High | 5 min
10. Verification | 10.6 | Verify TLS Configuration | Confirm TLS is properly configured | Check listener status shows ssl:default on 0.0.0.0:8883 | TLS listener active |  |  | Critical | 3 min
11. Documentation | 11.1 | Document Access URLs | Record all service endpoints | Dashboard, MQTT, MQTTS, WebSocket URLs | Documentation created |  |  | High | 10 min
11. Documentation | 11.2 | Document Credentials | Record admin credentials (securely) | Username, password, location | Credentials documented |  |  | Critical | 5 min
11. Documentation | 11.3 | Create Deployment Summary | Write deployment summary report | Include architecture, resources, tests | Summary created |  |  | High | 15 min
11. Documentation | 11.4 | Document Configuration Files | Save all YAML files | emqx-op.yaml, secrets, ingress configs | Files backed up |  |  | High | 5 min
11. Documentation | 11.5 | Create Testing Guide | Document testing procedures | Include MQTT and MQTTS test commands | Guide created |  |  | Medium | 10 min
12. Post-Deployment | 12.1 | Setup Monitoring | Configure monitoring for EMQX | Integrate with Prometheus/Grafana | Monitoring active |  |  | Medium | 30 min
12. Post-Deployment | 12.2 | Configure Alerts | Set up alerting for critical events | Configure alert rules | Alerts configured |  |  | Medium | 20 min
12. Post-Deployment | 12.3 | Setup Backup Strategy | Configure backup for EMQX data | Define backup schedule and location | Backup configured |  |  | High | 20 min
12. Post-Deployment | 12.4 | Document Troubleshooting | Create troubleshooting guide | Common issues and solutions | Guide created |  |  | Medium | 15 min
12. Post-Deployment | 12.5 | Production Readiness Review | Final review before production | Checklist review with senior | Review completed |  |  | Critical | 30 min

## CheckList
Phase | Task Name | Description | Command/Action | Expected Result
0. Server Setup | Check Server Access | Verify SSH access to all servers | ssh user@server-ip | SSH login successful
0. Server Setup | Update System Packages | Update package lists | sudo apt update | Package lists updated
0. Server Setup | Upgrade System Packages | Upgrade installed packages | sudo apt upgrade -y | Packages upgraded
0. Server Setup | Install Essential Tools | Install basic utilities | sudo apt install -y curl wget git vim net-tools | Tools installed
0. Server Setup | Check Internet Connectivity | Test internet connection | ping -c 4 8.8.8.8 | Packets received
0. Server Setup | Check DNS Resolution | Test DNS is working | nslookup google.com | DNS resolution successful
0. Server Setup | Set Hostname | Configure server hostname | sudo hostnamectl set-hostname node1 | Hostname set
0. Server Setup | Update /etc/hosts | Add server entries to hosts file | sudo vi /etc/hosts | Hosts file updated with all nodes
0. Server Setup | Disable Swap | Disable swap for Kubernetes | sudo swapoff -a && sudo sed -i '/ swap / s/^/#/' /etc/fstab | Swap disabled
0. Server Setup | Configure Firewall | Allow required ports | sudo ufw allow 22,6443,2379,2380,10250,10251,10252,30000:32767/tcp | Firewall configured
0. Server Setup | Install Python3 | Install Python for Ansible | sudo apt install -y python3 python3-pip | Python3 installed
0. Server Setup | Check Time Sync | Verify time synchronization | timedatectl | NTP synchronized: yes
1. Kubespray Setup | Clone Kubespray | Download Kubespray from GitHub | git clone https://github.com/kubernetes-sigs/kubespray.git | Kubespray cloned
1. Kubespray Setup | Install Ansible | Install Ansible on control node | sudo apt install -y ansible | Ansible installed
1. Kubespray Setup | Install Kubespray Requirements | Install Python dependencies | cd kubespray && sudo pip3 install -r requirements.txt | Requirements installed
1. Kubespray Setup | Copy Inventory Sample | Create inventory for your cluster | cp -rfp inventory/sample inventory/mycluster | Inventory created
1. Kubespray Setup | Configure Inventory | Define cluster nodes | vi inventory/mycluster/inventory.ini | Nodes configured (masters, workers, etcd)
1. Kubespray Setup | Set SSH Key Access | Copy SSH key to all nodes | ssh-copy-id user@node-ip | SSH key access configured
1. Kubespray Setup | Test Ansible Connectivity | Verify Ansible can reach nodes | ansible -i inventory/mycluster/inventory.ini all -m ping | All nodes return pong
1. Kubespray Setup | Configure Cluster Variables | Edit cluster settings | vi inventory/mycluster/group_vars/k8s_cluster/k8s-cluster.yml | Cluster settings configured
1. Kubespray Setup | Configure Network Plugin | Set network plugin (Calico/Flannel) | Edit k8s-cluster.yml, set kube_network_plugin | Network plugin configured
2. K8s Deployment | Run Kubespray Playbook | Deploy Kubernetes cluster | ansible-playbook -i inventory/mycluster/inventory.ini cluster.yml -b | Kubernetes deployed
2. K8s Deployment | Setup kubectl Config | Copy kubeconfig to control machine | mkdir -p ~/.kube && sudo cp /etc/kubernetes/admin.conf ~/.kube/config && sudo chown $(id -u):$(id -g) ~/.kube/config | kubectl configured
2. K8s Deployment | Verify Cluster Status | Check cluster is accessible | kubectl cluster-info | Cluster info displayed
2. K8s Deployment | Check All Nodes | Verify all nodes are ready | kubectl get nodes | All nodes in Ready state
2. K8s Deployment | Verify System Pods | Check system pods are running | kubectl get pods -n kube-system | All system pods running
2. K8s Deployment | Test Pod Deployment | Deploy a test pod | kubectl run test-pod --image=nginx | Pod created successfully
2. K8s Deployment | Delete Test Pod | Remove test pod | kubectl delete pod test-pod | Pod deleted
3. Helm Setup | Download Helm | Get Helm installation script | curl https://raw.githubusercontent.com/helm/helm/main/scripts/get-helm-3 | bash
3. Helm Setup | Verify Helm Installation | Check Helm version | helm version | Helm version displayed
3. Helm Setup | Add Helm Stable Repo | Add stable chart repository | helm repo add stable https://charts.helm.sh/stable | Repository added
3. Helm Setup | Update Helm Repos | Update repository cache | helm repo update | Repositories updated
4. Longhorn Storage | Install iSCSI Tools | Install iSCSI client on all nodes | sudo apt install -y open-iscsi | iSCSI tools installed
4. Longhorn Storage | Start iSCSI Service | Enable and start iSCSI | sudo systemctl enable --now iscsid | iSCSI service running
4. Longhorn Storage | Install NFSv4 Client | Install NFS client on all nodes | sudo apt install -y nfs-common | NFS client installed
4. Longhorn Storage | Add Longhorn Helm Repo | Add Longhorn chart repository | helm repo add longhorn https://charts.longhorn.io | Longhorn repo added
4. Longhorn Storage | Update Helm Repos | Update repository cache | helm repo update | Repositories updated
4. Longhorn Storage | Create Longhorn Namespace | Create namespace for Longhorn | kubectl create namespace longhorn-system | Namespace created
4. Longhorn Storage | Install Longhorn | Deploy Longhorn storage | helm install longhorn longhorn/longhorn --namespace longhorn-system | Longhorn installed
4. Longhorn Storage | Wait for Longhorn Ready | Wait for all pods to be ready | kubectl -n longhorn-system get pod -w | All pods running
4. Longhorn Storage | Verify Storage Class | Check Longhorn storage class | kubectl get sc | longhorn storage class exists
4. Longhorn Storage | Set Default Storage Class | Make Longhorn default | kubectl patch storageclass longhorn -p '{""metadata"": {""annotations"":{""storageclass.kubernetes.io/is-default-class"":""true""}}}' | Default class set
4. Longhorn Storage | Test PVC Creation | Test persistent volume claim | kubectl apply -f test-pvc.yaml | PVC created and bound
5. Ingress Setup | Add Nginx Ingress Repo | Add ingress-nginx chart repository | helm repo add ingress-nginx https://kubernetes.github.io/ingress-nginx | Ingress repo added
5. Ingress Setup | Update Helm Repos | Update repository cache | helm repo update | Repositories updated
5. Ingress Setup | Install Nginx Ingress | Deploy ingress controller | helm install ingress-nginx ingress-nginx/ingress-nginx --namespace ingress-nginx --create-namespace | Ingress controller installed
5. Ingress Setup | Wait for Ingress Ready | Wait for ingress pods ready | kubectl wait --namespace ingress-nginx --for=condition=ready pod --selector=app.kubernetes.io/component=controller --timeout=120s | Ingress controller ready
5. Ingress Setup | Verify Ingress Service | Check ingress service | kubectl get svc -n ingress-nginx | Ingress service created
5. Ingress Setup | Get Ingress External IP | Get LoadBalancer IP | kubectl get svc ingress-nginx-controller -n ingress-nginx | External IP assigned
6. MetalLB Setup | Check MetalLB Compatibility | Verify no cloud LB is present | kubectl get svc --all-namespaces | No cloud LoadBalancer
6. MetalLB Setup | Install MetalLB | Deploy MetalLB via manifest | kubectl apply -f https://raw.githubusercontent.com/metallb/metallb/v0.14.3/config/manifests/metallb-native.yaml | MetalLB installed
6. MetalLB Setup | Wait for MetalLB Ready | Wait for pods to be ready | kubectl wait --namespace metallb-system --for=condition=ready pod --selector=app=metallb --timeout=90s | MetalLB pods ready
6. MetalLB Setup | Create IP Address Pool | Configure IP range for LoadBalancer | kubectl apply -f metallb-ippool.yaml | IP pool created
6. MetalLB Setup | Create L2Advertisement | Configure Layer 2 advertisement | kubectl apply -f metallb-l2.yaml | L2 advertisement created
6. MetalLB Setup | Verify MetalLB Config | Check MetalLB configuration | kubectl get ipaddresspool -n metallb-system | IP pool configured
6. MetalLB Setup | Test LoadBalancer Service | Create test LoadBalancer service | kubectl apply -f test-lb-service.yaml | External IP assigned
7. Cert Manager | Add Cert-Manager Repo | Add cert-manager chart repository | helm repo add jetstack https://charts.jetstack.io | Cert-manager repo added
7. Cert Manager | Update Helm Repos | Update repository cache | helm repo update | Repositories updated
7. Cert Manager | Install CRDs | Install cert-manager CRDs | kubectl apply -f https://github.com/cert-manager/cert-manager/releases/download/v1.13.0/cert-manager.crds.yaml | CRDs installed
7. Cert Manager | Create Namespace | Create cert-manager namespace | kubectl create namespace cert-manager | Namespace created
7. Cert Manager | Install Cert-Manager | Deploy cert-manager | helm install cert-manager jetstack/cert-manager --namespace cert-manager --version v1.13.0 | Cert-manager installed
7. Cert Manager | Verify Installation | Check cert-manager pods | kubectl get pods -n cert-manager | All pods running
7. Cert Manager | Create ClusterIssuer | Create Let's Encrypt issuer | kubectl apply -f letsencrypt-issuer.yaml | ClusterIssuer created
8. Monitoring Setup | Add Prometheus Repo | Add prometheus-community repo | helm repo add prometheus-community https://prometheus-community.github.io/helm-charts | Prometheus repo added
8. Monitoring Setup | Update Helm Repos | Update repository cache | helm repo update | Repositories updated
8. Monitoring Setup | Create Monitoring Namespace | Create namespace for monitoring | kubectl create namespace monitoring | Namespace created
8. Monitoring Setup | Install kube-prometheus-stack | Deploy Prometheus and Grafana | helm install kube-prometheus-stack prometheus-community/kube-prometheus-stack --namespace monitoring | Monitoring stack installed
8. Monitoring Setup | Wait for Pods Ready | Wait for monitoring pods | kubectl wait --namespace monitoring --for=condition=ready pod --all --timeout=300s | All pods ready
8. Monitoring Setup | Verify Prometheus Service | Check Prometheus service | kubectl get svc -n monitoring | grep prometheus
8. Monitoring Setup | Verify Grafana Service | Check Grafana service | kubectl get svc -n monitoring | grep grafana
8. Monitoring Setup | Get Grafana Password | Retrieve Grafana admin password | kubectl get secret -n monitoring kube-prometheus-stack-grafana -o jsonpath='{.data.admin-password}' | base64 -d
8. Monitoring Setup | Expose Grafana | Create ingress for Grafana | kubectl apply -f grafana-ingress.yaml | Grafana accessible
9. SSL Certificates | Locate SSL Certificates | Find existing SSL certificates | ls -la /path/to/ssl/ | Certificate files found
9. SSL Certificates | Verify Certificate Validity | Check if certificates are valid | openssl x509 -in cert.crt -text -noout | Certificate details displayed
9. SSL Certificates | Create TLS Secret | Create Kubernetes TLS secret | kubectl create secret tls emqx-tls --cert=cert.crt --key=cert.key -n platform | Secret created
9. SSL Certificates | Verify Secret Creation | Confirm TLS secret exists | kubectl get secret emqx-tls -n platform | Secret found
10. Namespace Setup | Create Platform Namespace | Create namespace for EMQX | kubectl create namespace platform | Namespace created
10. Namespace Setup | Verify Namespace | Check namespace exists | kubectl get namespace platform | Namespace active
10. Namespace Setup | Set Resource Quotas | Configure namespace quotas | kubectl apply -f platform-quota.yaml | Quotas configured
10. Namespace Setup | Set Network Policies | Configure network policies | kubectl apply -f platform-netpol.yaml | Network policies set
11. EMQX Operator | Add EMQX Helm Repo | Add EMQX chart repository | helm repo add emqx https://repos.emqx.io/charts | Repository added
11. EMQX Operator | Update Helm Repos | Update repository cache | helm repo update | Repository updated
11. EMQX Operator | Create Operator Namespace | Create namespace for EMQX operator | kubectl create namespace emqx-operator-system | Namespace created
11. EMQX Operator | Install EMQX Operator | Deploy EMQX operator | helm install emqx-operator emqx/emqx-operator -n emqx-operator-system --create-namespace | Operator installed
11. EMQX Operator | Wait for Operator Ready | Wait for operator pods ready | kubectl wait --for=condition=Ready pod -l control-plane=controller-manager -n emqx-operator-system --timeout=300s | Pod ready
11. EMQX Operator | Verify Operator | Check operator pods running | kubectl get pods -n emqx-operator-system | All pods running
12. EMQX Config | Create EMQX YAML | Prepare emqx-op.yaml config | vi emqx-op.yaml | Config file created
12. EMQX Config | Configure Cluster Size | Set core/replicant nodes | Edit emqx-op.yaml replicas | Replicas configured (2 core, 1 replicant)
12. EMQX Config | Configure TLS Listeners | Configure MQTT/MQTTS/WS/WSS | Edit emqx-op.yaml listeners | TLS configured for 8883, 8084
12. EMQX Config | Configure Resources | Set CPU/memory limits | Edit emqx-op.yaml resources | Resources defined
12. EMQX Config | Configure Persistence | Set up persistent storage | Edit emqx-op.yaml volumeClaimTemplates | Storage configured
13. EMQX Deploy | Apply EMQX Config | Deploy EMQX cluster | kubectl apply -f emqx-op.yaml | EMQX resources created
13. EMQX Deploy | Monitor Pod Creation | Watch pods being created | kubectl get pods -n platform -w | Pods creating
13. EMQX Deploy | Wait for EMQX Ready | Wait for all pods ready | kubectl wait --for=condition=Ready pod -l apps.emqx.io/instance=emqx -n platform --timeout=600s | All pods ready
13. EMQX Deploy | Verify EMQX CR | Check EMQX custom resource | kubectl get emqx -n platform | EMQX running
13. EMQX Deploy | Check Pod Logs | Review logs for errors | kubectl logs emqx-core-0 -n platform | No critical errors
14. Service Exposure | Check Services | Verify EMQX services | kubectl get svc -n platform | Services created
14. Service Exposure | Configure LoadBalancer | Change to LoadBalancer type | kubectl patch svc emqx-dashboard -n platform -p '{""spec"":{""type"":""LoadBalancer""}}' | LoadBalancer IP assigned
14. Service Exposure | Verify LoadBalancer IPs | Check external IPs | kubectl get svc -n platform | grep emqx
14. Service Exposure | Setup Port Forward | Alternative access method | kubectl port-forward svc/emqx-dashboard -n platform 18083:18083 --address 0.0.0.0 & | Port forward active
14. Service Exposure | Configure Ingress | Setup ingress for dashboard | kubectl apply -f mqtt-dash-ingress.yaml | Ingress created
15. Testing | Access Dashboard | Open EMQX dashboard | http://<IP>:18083 | Dashboard accessible
15. Testing | Login Dashboard | Login with default creds | Username: admin, Password: public | Login successful
15. Testing | Check Cluster Status | Verify cluster nodes | Dashboard → Cluster → Overview | All nodes shown
15. Testing | Test MQTT via Dashboard | Use WebSocket client | Dashboard → Diagnose → WebSocket | Connection successful
15. Testing | Install mosquitto-clients | Install MQTT tools | sudo apt install -y mosquitto-clients | Tools installed
15. Testing | Test MQTT via CLI | Test MQTT connection | mosquitto_pub -h <IP> -p 1883 -t test/mqtt -m 'test' | Command successful
15. Testing | Extract CA Cert | Export CA certificate | kubectl get secret emqx-tls -n platform -o jsonpath='{.data.ca.crt}' | base64 -d > /tmp/emqx-ca.crt
15. Testing | Test MQTTS | Test TLS encryption | mosquitto_pub -h <IP> -p 8883 -t test/mqtts -m 'secure' --cafile /tmp/emqx-ca.crt --insecure | Command successful
15. Testing | Check Listeners | Verify all listeners active | kubectl exec -it emqx-core-0 -n platform -- emqx_ctl listeners | All listeners running
16. Verification | Verify All Pods | Check all pods healthy | kubectl get pods -n platform | All pods 1/1 or 2/2
16. Verification | Check Resources | Monitor CPU/memory | kubectl top pods -n platform | Resources within limits
16. Verification | Verify Storage | Check PVCs bound | kubectl get pvc -n platform | All PVCs bound
16. Verification | Test API | Test EMQX API | curl http://<IP>:18083/api/v5/nodes -u admin:public | API response received
16. Verification | Check Logs | Review for errors | kubectl logs -l apps.emqx.io/instance=emqx -n platform --tail=50 | No critical errors
16. Verification | Verify TLS Config | Confirm TLS configured | Check ssl:default on 0.0.0.0:8883 | TLS listener active
17. Documentation | Document URLs | Record service endpoints | Dashboard, MQTT, MQTTS URLs | Documentation created
17. Documentation | Document Credentials | Record admin credentials | Username, password, location | Credentials documented
17. Documentation | Create Summary | Write deployment summary | Architecture, resources, tests | Summary created
17. Documentation | Backup Configs | Save all YAML files | emqx-op.yaml, secrets, ingress | Files backed up
17. Documentation | Create Test Guide | Document test procedures | MQTT and MQTTS commands | Guide created
18. Post-Deploy | Setup Monitoring | Configure EMQX monitoring | Integrate with Prometheus/Grafana | Monitoring active
18. Post-Deploy | Configure Alerts | Setup alerting | Configure alert rules | Alerts configured
18. Post-Deploy | Setup Backups | Configure backup strategy | Define schedule and location | Backup configured
18. Post-Deploy | Document Troubleshooting | Create troubleshooting guide | Common issues and solutions | Guide created
18. Post-Deploy | Production Review | Final review | Review with senior | Review completed

## Commands
Command Category | Command / Example | What it Does / Usage | Typical Use Case / Notes
Kubernetes Cluster | kubectl get nodes | Shows all worker/master nodes and their readiness status | Cluster sanity check
Namespaces | kubectl get namespaces | Lists all namespaces in the cluster | Verify required namespaces
Namespace (create) | kubectl create namespace platform | Creates the "platform" namespace | Needed before deploying CRs
Pods (all) | kubectl get pods -A | Shows all pods in all namespaces | Global pod status
Pods (in namespace) | kubectl get pods -n platform | Shows pods just in the "platform" namespace | Quick EMQX pod status check
Pod logs | kubectl logs emqx-core-0 -n platform | Shows logs from a specific pod | Debugging
Pod details | kubectl describe pod emqx-core-0 -n platform | Detailed pod state, events, volumes | Deep debugging
Deploy YAML | kubectl apply -f emqx-op.yaml | Deploys or updates EMQX resources from YAML | Initial deployment/update
Delete YAML | kubectl delete -f emqx-op.yaml | Destroys resources from YAML | Purge for full rebuild
Pods (watch) | kubectl get pods -n platform -w | Watches real-time pod status changes | Rolling upgrades/troubleshooting
Get CRs | kubectl get emqx -n platform | See EMQX custom resources deployed | Operator-based status
Check Service | kubectl get svc -n platform | Lists all services in the platform namespace | Find ports/IPs for access
Patch to LoadBalancer | kubectl patch svc emqx-dashboard -n platform -p '{"spec":{"type":"LoadBalancer"}}' | Converts NodePort/ClusterIP service to LoadBalancer | Access dashboard externally
Watch Events | kubectl get events -n platform | Shows latest Kubernetes events in a namespace | Diagnosing issues
TLS Secret create | kubectl create secret tls emqx-tls --cert=cert.crt --key=cert.key -n platform | Upload SSL cert and key as a secret for TLS | Needed for secure MQTTS/HTTPS
List secrets | kubectl get secrets -n platform | Lists all secrets in a namespace | Validate TLS/creds upload
Extract secret | kubectl get secret emqx-tls -n platform -o jsonpath='{.data.ca\.crt}' ¦ base64 -d > ca.crt | Gets CA cert from secret, saves it locally | For mosquitto MQTTS testing
Ingress create | kubectl apply -f mqtt-dash-ingress.yaml | Applies an ingress for HTTP/S dashboard access | HTTPS with custom/CN cert
Operator install | helm repo add emqx https://repos.emqx.io/charts ; helm repo update ; helm install emqx-operator emqx/emqx-operator -n emqx-operator-system --create-namespace | Sets up EMQX Operator using Helm | Once per cluster/upgrade
List Helm releases | helm list -A | Shows all Helm-based installs in the cluster | Find Operator/component versions
Cluster-info | kubectl cluster-info | Shows Kubernetes master/services info | Cluster connectivity check
Service port-forward | kubectl port-forward svc/emqx-dashboard -n platform 18083:18083 --address 0.0.0.0 & | Exposes pod/service port to your workstation | For local dashboard/MQTT client tests
Delete pod | kubectl delete pod emqx-core-0 -n platform | Deletes (restarts) a pod | Fix stuck/broken pods
Manual rollout restart | kubectl rollout restart statefulset emqx-core -n platform | Restarts EMQX pods/statefulsets safely | After config/secret update
Get resource utilization | kubectl top pods -n platform | Shows CPU/Memory usage of all pods | Monitor resource health
Persistent volumes | kubectl get pvc -n platform | Lists all persistent volume claims | Validate storage is working
Get roles/bindings | kubectl get roles,rolebindings,clusterroles,clusterrolebindings -A | Lists security roles for access troubleshooting | RBAC/permission debugging
Check endpoints | kubectl get endpoints emqx-dashboard -n platform | Shows the endpoint IP:port for service | Networking issues
Exec shell | kubectl exec -it emqx-core-0 -n platform -- /bin/sh | Gets into the running container | Run CLI commands, debug
emqx_ctl listeners | kubectl exec -it emqx-core-0 -n platform -- emqx_ctl listeners | Shows MQTT/TLS/WS listener active status | Verify port/service health
emqx_ctl status | kubectl exec -it emqx-core-0 -n platform -- emqx_ctl status | Basic broker status (version, listeners, clusters, etc.) | High-level health
emqx_ctl cluster status | kubectl exec -it emqx-core-0 -n platform -- emqx_ctl cluster status | Shows cluster node members/roles | Distributed status check
emqx_ctl log | kubectl exec -it emqx-core-0 -n platform -- emqx_ctl log list | Lists available EMQX logs | Historical issue tracing
emqx_ctl plugins list | kubectl exec -it emqx-core-0 -n platform -- emqx_ctl plugins list | Lists all plugins and their states | Troubleshooting/debugging plugins
mosquitto_pub test | mosquitto_pub -h <host> -p 1883 -t test/mqtt -m 'hello' | Publishes a message to test topic | MQTT test
mosquitto_pub MQTTS | mosquitto_pub -h <host> -p 8883 -t test/mqtts -m 'secure' --cafile ca.crt --insecure | Publishes with TLS cert check disabled | MQTTS/SSL test
mosquitto_sub | mosquitto_sub -h <host> -p 1883 -t test/mqtt -v | Subscribes to a topic and prints published messages | Real-time MQTT test
curl HTTP API | curl -X POST 'http://<host>:18083/api/v5/publish' -u 'admin:public' -H 'Content-Type: application/json' -d '{"topic": "test", "payload": "dGVzdA==", "qos": 0}' | Publishes via dashboard HTTP API | Useful for APIs/manual
kubectl explain | kubectl explain emqx | Shows EMQX CRD field documentation | Decoding CRD structure
kubectl get all | kubectl get all -n platform | Lists all resources (svc, pod, deploy, etc.) in the namespace | General quick view
kubectl config get-contexts | kubectl config get-contexts | List all configured contexts (clusters) | Cluster/namespace awareness
kubectl set image | kubectl set image deployment/emqx-core emqx-core=emqx/emqx:5.0.26 -n platform | Updates deployment image version | Upgrade/downgrade broker version
helm uninstall | helm uninstall emqx-operator -n emqx-operator-system | Removes the operator cleanly | Teardown/refresh operator
emqx_ctl reload | kubectl exec -it emqx-core-0 -n platform -- emqx_ctl reload | Hot reloads config without restart | Fast config changes
kubectl cp | kubectl cp file platform/pod:/path | Copies a file to/from pod | Upload custom config/scripts